## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | An Application based Data-Driven AI Fitness Trainer integrating Deep Learning Algorithms and Computer Vision | [5 empty] | INSTITUTE NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE PROF. ANAGHA AHER | [6 empty] | DEPARTMENT NAME | [6 empty] | CSE DATA SCIENCE
[7 empty] | DATE | [6 empty] | 2024-10-22
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [39 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Major Project | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-08-02 | 2024-08-16 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Major Project | Sneha Sabat, Riya Sawant, Rutuja Patil, Tanvi Panchal | 2024-08-16 | 2024-08-23 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of project proposal. | Rutuja Patil, Sneha Sabat | 2024-08-30 | 2024-09-06 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
2 | Project Design and Implementation
2.1 | Creating models for Workout recommendation and Diet recommendation | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-09-06 |  |  | 80%
2.2 | Creating AI Virtual trainer with exercise detection and real-time feedback | Rutuja Patil, Riya Sawant | 2024-09-06 |  |  | 70%
2.3 | Integrating Application's Graphical User Interface | Rutuja Patil, Riya Sawant, Tanvi Panchal, Sneha Sabat | 2024-09-06 |  |  | 80%
2.4 | Presentation I | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-09-25 | 2024-10-02 | 2 | 100% | bar: WEEK 11 M to WEEK 13 F
SSA