## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: DefenseLedger – Blockchain-Powered Ammunition and Supply Chain | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(CSE-Data Science)
PROJECT GUIDE: Prof. Sarala Mary and Prof. Richa Singh | [6 empty] | DATE | [6 empty] | 2024-10-23
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the major project | Tanaya Patil, Ayush Mistry, Mayank Kumar, Sahil Mujumdar | 2024-02-08 | 8-16-24 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the major project | Tanaya Patil, Mayank Kumar | 8-16-24 | 8-23-24 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of a project proposal. | Ayush Mistry, Sahil Mujumdar | 8-30-24 | 2024-06-09 | 1 | 100% | bar: WEEK 4 M to WEEK 4 F
2 | Project Design and Implementation
2.1 | Designing the Graphical User Interface(GUI) for the admin side. | Tanaya Patil, Ayush Mistry | 2024-06-09 |  | 3 | 100% | bar: WEEK 5 M to WEEK 7 F
2.2 | Blockchain Integration for admin side. | Tanaya Patil, Sahil Mujumdar | 09-25-2024 |  | 2 | 100% | bar: WEEK 8 M to WEEK 10 F
2.3 | Integration of modules and Report Writing | Mayank Kumar, Ayush Mistry | 2024-10-01 | 10-22-24 | 3 | 100% | bar: WEEK 9 M to WEEK 12 F
2.4 | Presentation I | Tanaya Patil, Ayush Mistry, Mayank Kumar, Sahil Mujumdar | 09-25-24 | 2024-02-10 | 2 | 100% | bar: WEEK 13 M to WEEK 14 F